## Actual Plan
WEEK 0 | 2022-03-21 | DAY 0 | INTRODUCTION AND ASSESSMENT | Completed
| 2022-03-22 | DAY 1 | REQUIREMENT PHASE | Completed
| 2022-03-23 | DAY 2 |  | Completed
| 2022-03-24 | DAY 3 | DESIGN PHASE | Completed
| 2022-03-25 | DAY 4 |  | Completed
WEEK 1 | 2022-03-28 | DAY 5 | DESIGN PHASE | Completed
| 2022-03-29 | DAY 6 |  | Completed
| 2022-03-30 | DAY 7 | CODING AND TESTING PHASE | Completed
| 2022-03-31 | DAY 8 |  | Completed
| 2022-04-01 | DAY 9 | PROJECT MANAGEMENT | Completed
| 2022-04-02 | DAY 10 | PROJECT KICKOFF | Completed
WEEK 2 | 2022-04-04 | DAY 11 | SPRINT 0 - Requirements Phase | Completed
| 2022-04-05 | DAY 12 |  | Completed
| 2022-04-06 | DAY 13 |  | Completed
| 2022-04-07 | DAY 14 |  | Completed
| 2022-04-08 | DAY 15 |  | Completed
| 2022-04-09 | DAY 16 | SPRINT 1 - Design Phase | Completed
WEEK 3 | 2022-04-11 | DAY 17 | SPRINT 1 - Design Phase | Completed
| 2022-04-12 | DAY 18 |  | Completed
| 2022-04-13 | DAY 19 |  | Completed
WEEK 4 | 2022-04-20 | DAY 20 | SPRINT 1 - Design Phase | Completed
| 2022-04-21 | DAY 21 |  | Completed
| 2022-04-22 | DAY 22 | SPRINT 2 - Coding Phase | Completed
| 2022-04-23 | DAY 23 |  | Completed
WEEK 5 | 2022-04-25 | DAY 24 | SPRINT 2 - Coding Phase | Completed
| 2022-04-26 | DAY 25 |  | Completed
| 2022-04-27 | DAY 26
| 2022-04-28 | DAY 27 | SPRINT 3 - Coding Phase
| 2022-04-29 | DAY 28
| 2022-04-30 | DAY 29
WEEK 6 | 2022-05-05 | DAY 30 | SPRINT 3 - Coding Phase
| 2022-05-06 | DAY 31
| 2022-05-07 | DAY 32 | SPRINT 4 - Testing Phase
WEEK 7 | 2022-05-09 | DAY 33 | SPRINT 4 - Testing Phase
| 2022-05-10 | DAY 34
| 2022-05-11 | DAY 35
| 2022-05-12 | DAY 36
| 2022-05-13 | DAY 37 | SPRINT 5 - Finalizing Phase
| 2022-05-14 | DAY 38
WEEK 8 | 2022-05-16 | DAY 39 | SPRINT 5 - Finalizing Phase
| 2022-05-17 | DAY 40
| 2022-05-18 | DAY 41
| 2022-05-19 | DAY 42 | PROJECT REVIEW
| 2022-05-20 | DAY 43
| 2022-05-21 | DAY 44

## Revised Plan
Day | Date | Phase | Work
Monday | 2022-05-09 | Coding Phase | Web API + Angular Component Creation Completion | Completed(CRUD for user and profile) | In Progress (Share,Download,Request to update)
Tuesday | 2022-05-10 | Coding Phase | Web API + Angular Component Creation Completion | Completed(Login service)
Wednesday | 2022-05-11 | Coding Phase | Web API + Angular Component Creation Completion | Completed(Change Password service)
Thursday | 2022-05-12 | Coding Phase | Web API + Angular Component Creation Completion | Completed(Profile History)
Friday | 2022-05-13 | Coding Phase | Web API + Angular Component Creation Completion | Completed(all angular component creation)
Saturday | 2022-05-14 | Coding Phase | Web API + Angular Component Creation Completion | Completed(all angular component creation)
Week 20 | 2022-05-14 | Status | Send the status as per the given table
Sunday | 2022-05-15 | LEAVE
Monday | 2022-05-16 | Coding Phase | Angular and Web API Integration | Completed(HR flow) | In Progress(Personal details,Project in Wizard) | Yet to Start(share,download,request to update)
Tuesday | 2022-05-17 | Coding Phase | Angular and Web API Integration | Completed(Change Password,Login) | In Progress(Filters,View Profile,Profile history) | Yet to Start(profile approval by reporting person)
Wednesday | 2022-05-18 | Coding Phase | Angular and Web API Integration | Completed(Education,Skill,Achievement in Wizard)
Thursday | 2022-05-19 | Coding Phase | Angular and Web API Integration | Completed(cards page)
Friday | 2022-05-20 | Coding Phase | Angular and Web API Integration
Saturday | 2022-05-21 | Coding Phase | Angular and Web API Integration
Saturday | 2022-05-21 | Coding Phase | Angular and Web API Integration
Week 21 | 2022-05-22 | Status | Send the status as per the given table
Monday | 2022-05-23 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | Completed(User and Profile Controller) | In Progress(User DAL) | Yet to Start(Remaining)
Tuesday | 2022-05-24 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | Completed(User Service) |  | Yet to Start(Remaining)
Wednesday | 2022-05-25 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | Completed(Personal details and Education details) |  | Yet to Start(Remaining)
Thursday | 2022-05-26 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing |  |  | Yet to Start(Remaining)
Friday | 2022-05-27 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing |  |  | Yet to Start(Remaining)
Saturday | 2022-05-28 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing
Week 22 | 2022-05-28 | Status | Send the status as per the given table
Sunday | 2022-05-29 | LEAVE
Monday | 2022-05-30 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing |  |  | Yet to Start
Tuesday | 2022-05-31 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing |  |  | Yet to Start
Wednesday | 2022-06-01 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing |  |  | Yet to Start
Thursday | 2022-06-02 | Coding Phase | Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages) |  |  | Yet to Start
Friday | 2022-06-03 | Coding Phase | Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages) |  |  | Yet to Start
Saturday | 2022-06-04 | Coding Phase | Usability Testing - Lighthouse, https://validator.w3.org/ + Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages) |  |  | Yet to Start
Week 23 | 2022-06-04 | Status | Send the status as per the given table
Sunday | 2022-06-05 | LEAVE
Monday | 2022-06-06 | Testing Phase | Test Scenarios and Test Case Preparation |  |  | Yet to Start
Tuesday | 2022-06-07 | Testing Phase | Test Scenarios and Test Case Preparation |  |  | Yet to Start
Wednesday | 2022-06-08 | Testing Phase | Test Scenarios and Test Case Preparation |  |  | Yet to Start
Thursday | 2022-06-09 | Testing Phase | Application Testing and Defects Tracking and Fixing |  |  | Yet to Start
Friday | 2022-06-10 | Testing Phase | Application Testing and Defects Tracking and Fixing |  |  | Yet to Start
Saturday | 2022-06-11 | Testing Phase | Application Testing and Defects Tracking and Fixing |  |  | Yet to Start
Week 24 | 2022-06-11 | Status | Send the status as per the given table
Sunday | 2022-06-12 | LEAVE
Monday | 2022-06-13 | Testing Phase | Application Testing and Defects Tracking and Fixing |  |  | Yet to Start
Tuesday | 2022-06-14 | Testing Phase | Application Testing and Defects Tracking and Fixing |  |  | Yet to Start
Wednesday | 2022-06-15 | Testing Phase | Application Testing and Defects Tracking and Fixing |  |  | Yet to Start
Thursday | 2022-06-16 | Testing Phase | Application Testing and Defects Tracking and Fixing |  |  | Yet to Start
Friday | 2022-06-17 | Testing Phase | Application Testing and Defects Tracking and Fixing |  |  | Yet to Start
Saturday | 2022-06-18 | Testing Phase | Application Testing and Defects Tracking and Fixing |  |  | Yet to Start
Week 25 | 2022-06-18 | Status | Send the status as per the given table
Sunday | 2022-06-19 | LEAVE
Monday | 2022-06-20 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots |  |  | Yet to Start
Tuesday | 2022-06-21 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots |  |  | Yet to Start
Wednesday | 2022-06-22 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots |  |  | Yet to Start
Thursday | 2022-06-23 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots |  |  | Yet to Start
Friday | 2022-06-24 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots |  |  | Yet to Start
Saturday | 2022-06-25 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots |  |  | Yet to Start
Week 26 | 2022-06-25 | Status | Send the status as per the given table
Sunday | 2022-06-26 | LEAVE
Monday | 2022-06-27 | Review | Reviewing the Application of all above mentioned activities |  |  | Yet to Start
Tuesday | 2022-06-28 | Review | Reviewing the Application of all above mentioned activities |  |  | Yet to Start
Wednesday | 2022-06-29 | Review | Reviewing the Application of all above mentioned activities |  |  | Yet to Start
Thursday | 2022-06-30 | Review | Reviewing the Application of all above mentioned activities |  |  | Yet to Start
Friday | 2022-07-01 | Review | Reviewing the Application of all above mentioned activities |  |  | Yet to Start
Saturday | 2022-07-02 | LEAVE
Sunday | 2022-07-03 | LEAVE
Monday | 2022-07-04 | Demo | Demostration to Training and Delivery Team |  |  | Yet to Start
Tuesday | 2022-07-05 | Demo | Demostration to Training and Delivery Team |  |  | Yet to Start
Wednesday | 2022-07-06 | Demo | Demostration to Training and Delivery Team |  |  | Yet to Start
Thursday | 2022-07-07 | Summary | Refershing all the topics and Feedbacks |  |  | Yet to Start
Friday | 2022-07-08 | Summary | Refershing all the topics and Feedbacks |  |  | Yet to Start
Saturday | 2022-07-09 | LEAVE
Sunday | 2022-07-10 | LEAVE

## References
.NET Test Explorer | https://codemag.com/Article/2009101/Interactive-Unit-Testing-with-.NET-Core-and-VS-Code?msclkid=39ec497bd10a11ec9fc571f847c244bb
https://levelup.gitconnected.com/unit-testing-best-practices-in-net-c-3117ea4010b9?sk=5b4cdac557b3e56d97365669a12aa198
Angular - Testing | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_test.htm
Linting | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_lint.htm
Doumentation | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_doc.htm
Pipelines | https://docs.aws.amazon.com/codepipeline/latest/userguide/tutorials-four-stage-pipeline.html#tutorials-four-stage-pipeline-add-stage
Security Testing | Automated Security Testing Using OWASP ZAP with Examples! (swtestacademy.com)
Performance Testing | https://www.simplilearn.com/tutorials/jmeter-tutorial/jmeter-api-testing
https://www.youtube.com/watch?v=HiRZq9_xDjg
Code Analysis | https://www.c-sharpcorner.com/article/step-by-step-sonarqube-setup-and-run-sonarqube-scanner/

## Status Template - WEEK <No>
Work Items | Completed | In Progress | Yet to start
Low Level Design | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Web API Implementation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Angular Component Creation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Web API and Angular Integration | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Refactoring and Deployment | * Source Code Repo | * Source Code Repo | * Source Code Repo
Test Scenarios and Test Case Preparation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Application Testing and Defects Tracking and Fixing | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features

## Test Plan Template
<Project Name>Test Plan - <Cycle Number>
Scope of Test |  | Features Included | < Identify all software features and combinations of software features that will be tested.>
|  | Features Excluded | <Identify all features and significant combinations of features which will not be tested and the reasons.>
Test Deliverables |  |  | Identify the deliverable documents. You can list the following documents: - Test Plan - Test Cases - Test Incident Reports - Test Summary Reports>
Test Dependencies |  |  | <Identify significant constraints on testing, such as test-item availability, testing-resource availability, and deadlines.>
Test Environment |  | Hardware Environment | <Include the minimum hardware requirements that will be used to test the Application.>
Software Environment
Network and Communication
Test Items
S.No | Test Item |  | Source | [6 empty] | Version
Test Schedule
No. | Build | Features |  | Start Date | End Date | Actual Start Date | Actual End Date | Est Effort (in Hrs) | Actual Effort (in Hrs) | Completion % | Status
1
2
3
4
[5 empty] | Total |  | Total | 0 | 0 | #DIV/0!
Resources - Roles and Responsibilities
No. | Resource Name | Roles |  | Responsibilities
1
2
3
Depedencies
No. | Category | Description
1 | Software
2 | Resource
3 | Hardware
Assumptions
No. | Description
1
2
3

## Test Scenario Template
<Project Name><Smoke/Functional/Integration/ System/UAT> Test Scenarios
Type of Testing: Smoke/Functional/Integration/NFR/System Testing/UAT
Reference Documents :
Assumptions /Constraints :
Date:
Scenario ID | Requirement ID | Module/Feature | Scenario Description
Other details
Author:
Reviewed by:
Approved by:

## Test Case Template
<Project Name><Smoke/Functional/Integration/ System/UAT> Test Cases
Build/Release Version :
Type of Testing: Smoke/Functional/Integration/NFR/System Testing/UAT
Date:
Notes:
(Eg.) 1. This set of test cases should be run to check for the build fitness.
2. The tester should keep the back end (database) available and run an appropriate query to check the results / values displayed against the values shown in the front end.
Scenario ID | Test Case ID | Unit / Module or Location Description | Preconditions | Test Case Description | Test Steps | Test Data | Expected Result | Result (P/F/NT) | Defect ID | Comments
Other details
Author:
Reviewed by:
Approved by:
Test Results Reviewed by:

## Defect Log Template
Defect/Bug Report
Account/ Program Name
Project Name:
Defect Id(Required) | Defect Title | Detailed Defect Description | Related Module/Component | Defect Status | Defect Severity | Defect Priority | Defect Environment | Defect Injected Phase | Detected By | Detected in Phase | Detected in Version/Build | Defect Detected On Date | Fixed in version/Build No | Defect Category | Assigned to | Fixed on Date | Estimated Time To fix | Actual Time to Fix | Reopen Count
1 | ABC | [6 empty] | Requirements
2 | DEF | [6 empty] | Requirements
3 | GHI | [6 empty] | Analysis
4 | JKL | [6 empty] | Design
5 | MNO | [6 empty] | coding
5 | PQR | [6 empty] | Release
[26 empty] | Root cause | Communication Gap
[20 empty] | Defect Status |  | Defect Severity- | Defect Priority | Defect Environment |  |  | Lack of Domain Knowledge
[20 empty] | New |  | Critical | High | Development |  |  | Competency
[20 empty] | Open |  | Major | Critical | Integration Testing |  |  | Lack of EndUser Input
[20 empty] | Assigned |  | Minor | Medium | System Testing |  |  | Lack of Standards and Guidelines
[20 empty] | Fixed |  | Trivial | Low | Pre-Production |  |  | Environment
[20 empty] | Closed |  |  |  | UAT |  |  | Requirements not captured
[20 empty] | Rejected |  | Defect Type |  | Production |  |  | Requirements captured incorrectly
[20 empty] | Deferred |  | Review |  |  |  |  | Incomplete screen design
[22 empty] | Testing |  |  |  |  | Incorrect screen design
Incomplete database design
Incorrect database design
Incomplete report layout
Incorrect report layout
Incomplete interface definition
Incorrect interface definition
[20 empty] | Defect Injected Phase | Maintenance: | Development | Detected By | Defect Category | Missed Requirements |  | Incomplete security design
[21 empty] | Requirements | Requirements | QA |  | UI Issues |  | Incorrect security design
[21 empty] | Analysis | Design | Internal Customer |  | Functional Issues |  | Incorrect functionality
[21 empty] | Design | Coding | External Customer |  | Performance Issues |  | Incorrect / not optimized SQL
[21 empty] | coding | Release | Development |  | Non Functional |  | Incorrect logic in design
[21 empty] | Release |  |  |  | Security |  | Incomplete Unit Test Cases
[25 empty] | Environment Issues |  | Incorrect Unit Test Cases
[25 empty] | Upgrade Issue |  | Incomplete Integration Test Cases
[25 empty] | Database connectivity issues |  | Incorrect Integration Test Cases
[25 empty] | Cosmetic issues(Its Comes for Spelling Mistakes and color changes in prompts, It is like minimal changes/) |  | Incomplete Functional Test Cases
[25 empty] | Database Error |  | Incorrect Functional Test Cases
[25 empty] | Data Error |  | Code missing
[25 empty] | Typo Error |  | Incorrect logic in code
Exception handling error
Not a Defect
Incomplete Documentation
Incorrect Documentation
Scope Change
Recommendation
Incorrect Test Data